SOUTH EASTERN KENYA UNIVERSITY

UNIVERSITY EXAMINATIONS 2013/2014

THIRD YEAR FIRST SEMESTER EXAMINATION FOR THE DEGREE OF BACHELOR OF INFORMATION TECHNOLOGY

BIT 306: INFORMATION TECHNOLOGY PROJECT MANAGEMENT

DATE:	9/9/2013			 TIME:11:00-1:00 ( 2 HOURS)

INSTRUCTIONS TO CANDIDATES

- Answer questions ONE from section A(Compulsory)

- Answer ANY TWO questions from section  B

SECTION A(30 marks) Compulsory

Question One

(a)	(i)	Outline two advantages of using project management techniques. 	(2 marks)

    - Better control of financial, physical, and human resources

    - Improved customer relations

    - Shorter development times

    - Lower costs

    - Higher quality and increased reliability

    - Higher profit margins

    - Improved productivity

    - Better internal coordination

    - Higher worker morale

(ii)	Distinguish between system philosophy and system analysis as used in project management. 								(4 marks)

(b)	(i)	Explain the term project acquisition as used in project management.

(2 marks)

It involves project implementation and close-out phases of project development. Focuses on the delivery of the actual work of the project.

(ii)	With the aid of a diagram, describe the typical phases of project development. 											(4 marks)

- Concept phase-managers briefly describe the project. A preliminary or rough cost estimate of the project is done.

- Development phase-The project team creates more detailed project plans, a more accurate cost estimate, and a more thorough WBS

- Implementation phase-the project team creates a definitive or very accurate cost estimate, delivers the required work and provides performance reports to stakeholders.

- Close-out-all of the work is completed and acceptance of the project is done. The project team documents their experiences.

(c)	 (i)	Joseph would like to plan for an information system project. He decides to use

the activity-based WBS. With the aid of a diagram, outline the possible plan.

(4 marks)

(ii)	Outline two advantages of the approach in (i).			(2 marks)

You can be able to obtain a complete task catalogue with non-overlapping tasks.

It suggests the dependencies among the activities

(d) 	Peter intends to start a small ICT business enterprise.  In his proposal, he projected the business to generate profits as follows: Sh 30,000 in year 1, Ksh. 50,000 in year 2, Ksh. 50,000 in year 3, Ksh. 80,000 in year 4 and Ksh. 200,000 in year 5.  Using a discount factor of 7% per annum, calculate the net present value assuming that Peter had invested Sh. 300,000 at the start of the business.				(5 marks)

(e)	Risks are unforeseen issues that cause a project to be delayed or over-budgeted.

Explain two risk factors common with ICT projects.				(4 marks)

- Supplier factors. Delayed supply of equipments, instability of hardware.

- Application factors. The nature and expected size of the application.

- Staff factors. Experience and skills, appropriateness of experience, staff turn-over rates, staff satisfaction.

- Project factors. Ill defined and unclear project objectives. Ill defined and unstructured project methods.

.

(f)	With aid of a diagram, describe a Gantt chart as used in project monitoring.

An activity bar chart showing the activities, their scheduled dates and duration, the reported progress of the activities; ‘today cursor’

(3 marks)

SECTION B (40 MARKS)  Answer two questions from this section

Question Two

(a)	With the aid of an example, describe Responsibility Assignment Matrix (RAM) as

used in project management.							(4 marks)

(b)	Differentiate between the following as used in project management:

- concept and development phases;

The project manager briefly describes the project and a rough cost estimate is done in the concept phase. An overview of the work involved is created.

Development phase-The project creates a more accurate cost estimate, more detailed project plans and a thorough WBS

(ii)	Project schedule and activity plan. 																	(4 marks)

Project schedule is a plan that shows the dates when each activity should start and stop and when and what resources will be required.

An activity plan describes how each activity will be undertaken.

(c)	Table 1shows the activities undertaken in an IT project. Use it to answer the question

that follows.

| Activity | Preceeding activity | Time in days |
| --- | --- | --- |
| A | - | 8 |
| B | - | 10 |
| C | - | 6 |
| D | A, B | 8 |
| E | B, C | 9 |
| F | C | 14 |
| G | D, E | 14 |
| H | F, G | 6 |

Table 1

- Draw an AoA network diagram to represent the execution of the activities. 									(5 marks)

- Determine the critical activities.					(3 marks)

Question Three

(a)	(i)	Distinguish between functional and matrix organization structures.	(4 marks)

In functional structure Functional managers or vice presidents in specialties such as engineering, manufacturing, information technology (IT), and human resources (HR) report to the chief executive officer (CEO).

Their staffs have specialized skills in their respective disciplines

In matrix organization structure, personnel report to a functional manager and one or two project managers. Project managers in matrix organizations have staff from various functional areas working on their projects

(ii)	SEKU intends to start an information system project for the finance

department. The project manager has decided to use the project evaluation and

review technique (PERT) to plan this project.

I.	Explain three disadvantages of this approach in respect to the project at

hand.								(6 marks)

- Time and labor intensive

- Assumption of unlimited resources is big issue

- Lack of functional ownership of estimates

- Mostly only used on large, complex projects

II.	Explain two levels at which the project size could be estimated.

(2 marks)

(b)	Your company has decided to use a new rapid development method for an IT project.

(i)	Outline two activities that could be carried out to manage the possible risks.

(2 marks)

- Risk planning-making contingency plans

- Risk control-Minimizing and reacting to problems arising from risks throughout the project

- Risk directing and staffing-Risk aversion strategies and problem solving strategies frequently involve the use of additional staff and this must be planned for and should be considered.

(ii)	Explain three strategies you could employ to reduce the risks associated

with the project.  							(6 marks)

- Hazard prevention- Prevent a hazard from occurring or reduce its likelihood to an insignificant level

- Likelihood reduction- Reduce the likelihood of an unavoidable risk by prior planning

- Risk avoidance- Some hazards cannot be avoided but their risks may

- Risk transfer- The impact of the risk can be transferred away from the project by contracting out or taking out insurance

- Contingency planning- Contingency plans are needed to reduce the impact of those risks that cannot be avoided

Question Four

(a)	Explain the following prioritization techniques used in resource allocation:

(i)	Total float; resources Ordered according to their total float. Smallest total float has highest priority. Activities are allocated resources in ascending order of total float.

- Ordered list. Activities that can proceed at the same time are ordered according to a set of simple criteria.

Burman’s priority list takes into account activity duration as well as total float:

- Shortest critical activity.

- Critical activities.

- Shortest non-critical activity.

- Non-critical activity with least float.

- Non-critical activities.

(4 marks)

(b)	Rosa was advised that project monitoring is essential because it guarantees project

success.

- Describe the most appropriate tool that she could use to monitor project cost.

(2 marks)

Earned value analysis-Calculate the earned value of each activity

Earned value=duration of an activity/total duration of the project

(ii)	Explain three possible actions she could undertake to bring the project back

to the target.								(6 marks)

- Shorten the critical activities. Assign more resources and put pressure on staff to work for longer hours.

- Re-order the activities. Relax the constraints on the start of an activity before the completion of the previous one

Subdivide the components of an activity so that they can be done in parallel

(c)	Discuss the Herzberg’s motivation theory as used in project management.	(8 marks)

Largely based in organizations

There are two kinds of motivational factors

- De-motivators. Examples of de-motivators

  - Company Benefits or Culture

  - Job Security

  - Work Conditions

  - Salary [or perceived inequity of]

  - Interpersonal or Team relations

Absence of de-motivators meant people did a fair days work

- High performance motivators. Examples of high performance motivators

  - Opportunity for growth

  - Nature of work tasks

  - Responsibility

  - Recognition

  - A sense of achievement

  - Autonomy

END

# Text boxes

Project feasibility

Project acquisition

Concept

Development

Implementation

Close-out

Software project

Requirements analysis

System design

Coding

Testing

Data design

Process

design