JARAMOGI OGINGA ODINGA UNIVERSITY OF SCIENCE AND TECHNOLOGY

SCHOOL OF AGRICULURE AND FOOD SCIENCE

UNIVERSITY EXAMINATION FOR THE DEGREE OF BACHELOR OF SCIENCE IN AGRIBUSINESS MANAGEMENT

3RD     YEAR  1ST    SEMESTER  2016/2017 ACADEMIC YEAR

MAIN

COURSE CODE: AAE 3312

COURSE TITLE: ANALYSIS AND PLANNING OF AGRICULTURAL PROJECTS

EXAM VENUE:LR9                                      STREAM: (BSc. Agribusiness Mgt. )

DATE: 13/4/17		    		  EXAM SESSION: 2.00 – 4.00PM

TIME:  2 HOURS

Instructions:

- Answer ALL questions in Section A and any other 2 questions in Section B .

- Candidates are advised not to write on the question paper.

- Candidates must hand in their answer booklets to the invigilator while in the examination room.

SECTION A		[30 MARKS]

Answer ALL questions in this Section.

- Project managers have a list of actions in a project and also specific results

from the actions. Give these actions and results required in a table form with

examples in the agricultural environment.					      [10 marks]

- The project concept has increasingly been used as an instrument to promote

development and change. In fact, a good and well designed project can be

the ‘cutting edge’ in a development strategy.

- Outline and explain five virtues of the development project approach

that makes it useful as a tool for rural socioeconomic development.          [5marks]

- Describe the project management process and different project phases

in project selection. 							         [5marks]

- Project managers must engage in risk management to understand and control

the risks in their projects.

- Explain the risk management process in a project. Illustrate where

necessary.								         [5marks]

- Differentiate between;

- Financial analysis and Economic analysis			         [1 mark]

- Ex-ante and Ex-post impact assessment			         [1 mark]

- Monitoring and Evaluation					         [1 mark]

- Justify the use of shadow prices in economic analysis		         [2marks]

SECTION B		[40 MARKS]

Answer any TWO QUESTIONS in this Section.

- The table below shows a hypothetical cost-benefit analysis (CBA) of a beef project. Use it to answer the following questions.

| Year | Total benefits ($m) | Total Cost ($m) | Net Benefits ($m) | NPV at 5% ($m) |
| --- | --- | --- | --- | --- |
| 0 | 0.00 | 450.00 |  |  |
| 1 | 0.00 | 450.00 |  |  |
| 2 | 0.00 | 450.00 |  |  |
| 3 | 357.01 | 225.00 |  |  |
| 4 | 360.86 | 225.00 |  |  |
| 5 | 364.46 | 225.00 |  |  |
| 6 | 367.82 | 225.00 |  |  |
| 7 | 370.96 | 225.00 |  |  |
| 8 | 373.89 | 225.00 |  |  |
| 9 | 376.61 | 225.00 |  |  |
| 10 | 379.15 | 225.00 |  |  |
| 11 | 381.52 | 225.00 |  |  |
| 12 | 383.72 | 225.00 |  |  |
| 13 | 385.76 | 225.00 |  |  |
| 14 | 387.66 | 225.00 |  |  |
| 15 | 608.09 | 225.00 |  |  |
| Total | 5,097.53 | 4,275.00 |  |  |

- Complete the undiscounted net benefits column, clearly highlighting

the total undiscounted net benefits.					         [5marks]

- How do the total undiscounted net benefits compare to the discounted

net benefits, when net benefits are discounted at 5%?		         [5marks]

- Suppose you were required to appraise this project, would you use the

discounted total net benefits or the undiscounted total net benefits?

Provide economic justification for your answer.			         [5marks]

- Explain how you would use the cost-benefit ratio to appraise this project.

(please do not calculate)						         [5marks]

- A local sugar company has been experiencing problems with transportation of sugar cane from the production site to the processing site. There has been high frequency of truck accidents due to careless driving, poor conditions of vehicles and impassable feeder roads. The trucks have not been serviced for some time now due to negative cash flows. All these have translated into high absenteeism, high insurance premiums and delay in cane delivery. Prepare a simple logical framework proposal for this scenario: develop

- A problem tree, 							         [4marks]

- An objective tree, 							         [4marks]

- A strategy tree and							         [4marks]

- Log frame matrix. 							         [8marks]

- Use the table below to answer the questions.

| Activity | Predecessor | Duration (Days) |
| --- | --- | --- |
| A | - | 6 |
| B | A | 8 |
| C | A | 8 |
| D | B | 20 |
| E | B | 18 |
| F | C | 10 |
| G | E | 8 |
| H | D,F | 2 |
| I | G,H | 7 |

Required;

- Draw a network diagram							[8marks]

- Determine;

- Critical activities							[2marks]

- Critical path							[2marks]

- Project duration							[2marks]

- What is the probability of finishing the project in 55 days	[2marks]

- Explain some of the main features of agricultural development projects.[4marks]