MERU UNIVERSITY OF SCIENCE AND TECHNOLOGY

P.O. Box 972-60200 – Meru-Kenya.

Tel: 020-2069349, 061-2309217. 064-30320 Cell phone: +254 712524293, +254 789151411

Fax: 064-30321

Website: www.must.ac.ke  Email: info@must.ac.ke

University Examinations 2015/2016

THIRD YEAR, FIRST SEMESTER EXAMINATION FOR THE DIPLOMA IN CIVIL ENGINEERING

ECV 2306: PROJECT MANAGEMENT II.

DATE: AUGUST 2016                                                                                     TIME: 11/2 HOURS

INSTRUCTIONS: -	Answer question one and any other two questions

QUESTION ONE (30 MARKS)

- Define planning in project management						(1 mark)

- Identify six steps that are followed when planning for any project			(6 marks)

- Describe the difference between a work breakdown structure and an organization breakdown structure.										(4 marks)

- When carrying out project planning, explain why it is beneficial to consider the resources in the determination of the logical relationship among activities that use the same resources.												(2 marks)

- Describe two differences between AOA and AON modes of representation as used in the generation of an activity network diagram 						(4 marks)

- Discuss two advantages of AOA 							(2 marks)

- Explain the importance of a WBS in project management.				(6 marks)

- Explain five characteristics of a project.						(5 marks)

QUESTION TWO (15 MARKS)

- (i) Define CPM 									(2 marks)

(ii) Discuss the limitations of CPM method of scheduling 				(5 marks)

- Given the following information

| ACTIVITY | PRECEDING ACTIVITY | DURATION |
| --- | --- | --- |
| A B C D E F G H | - A A B B,C E D,F G | 2 10 8 10 7 9 3 5 |

Draw the network diagram and determine the critical path and duration for the project.	(8 marks)

QUESTION THREE (15 MARKS)

- Outline two main reasons why time-cost trade-off is necessary in project management.												(2 marks)

- Explain the three forms of scheduling 						(6 marks)

- Describe the three mechanisms for project control					(6 marks)

- Explain one advantage of scheduling.						(1 mark)

QUESTION FOUR (15 MARKS)

- List three advantages of resource levelling.						(3 marks)

- Discuss the limitations of network analysis.						(4 marks)

- Discuss the shortcomings of the PERT method					(4 marks)

- List four advantages of bar charts.							(4 marks)