MAASAI MARA UNIVERSITY

REGULAR UNIVERSITY EXAMINATIONS

2016/2017 ACADEMIC YEAR

THIRD YEAR SECOND SEMESTER

SCHOOL OF BUSINESS AND ECONOMICS

BACHELOR OF ARTS ECONOMICS

COURSE CODE: ECO 315

COURSE TITLE:  QUANTITATIVE METHODS II

DATE:  7TH JULY 2017			       	TIME:  0830 – 1030 HRS

INSTRUCTIONS TO CANDIDATES

Answer Question ONE and any other THREE questions

This paper consists of FOUR  printed pages. Please turn over.

QUESTION ONE

Briefly, define the following terms:

a) Queue jockeying 						[5 marks]

b) Degenerate solution 						[5 marks]

c) Slack variable							 [5 marks]

d) Dynamic programming 					[5 marks]

e) Gantt Chart 							[5 marks]

QUSTION TWO

Solve the following linear programming problem graphically. 												[15 Marks]

Maximize Z = 100X1 + 50X2

Subject to:

4X1 + 6X2≤24

X1≤4

X2≤4/3

X1, X2≤0

QUESTION THREE

The arrival rate of customers at a banking counter follows Poisson distribution with a mean of 45 per hour. The service rate of the counter clerk also follows Poisson distribution with a mean of 60 per hour.

a) What is the probability of having 0 customers in the system (p0)? 													[3 Marks]

b) What is the probability of having 5 customers in the system (p5)?												[3 Marks]

c) What is the probability of having 10 customers in the system (p10)? 												[3 Marks]

d) Find Ls, Lq, Ws and Wq. 						[6 Marks]

QUESTION FOUR

The annual demand of an item in a leading supermarket in Kenya is 9000 units. Its annual carrying cost is 15% of the purchase price of the item per year, where the purchase price is Shs 20 per unit. The ordering cost is Shs 15 per order. Presently the order size of the item is the average monthly demand of that item.

a) Find the economic order quantity 				[8 Marks]

b) Compare its cost with the present ordering system and find the corresponding cost advantage if it exists. 				[7 Marks]

QUESTION FIVE

The table below summarizes the details of a project involving 14 activities

| Activity | Immediate Predecessor(s) | Duration (months) |
| --- | --- | --- |
| A | - | 2 |
| B | - | 6 |
| C | - | 4 |
| D | B | 3 |
| E | A | 6 |
| F | A | 8 |
| G | B | 3 |
| H | C,D | 7 |
| I | C,D | 2 |
| J | E | 5 |
| K | F,G,H | 4 |
| L | F,G,H | 3 |
| M | I | 13 |
| N | J,K | 7 |

a) Construct the critical path method (CPM). 				[5 marks]

b) Determine the critical path and project completion time. 		[5 Marks]

c) Compute total floats and free floats for non-critical activities. 	[5 Marks]

//END