MAASAI MARA UNIVERSITY

REGULAR UNIVERSITY EXAMINATIONS

2016/2017 ACADEMIC YEAR

FOURTH YEAR SECOND SEMESTER

SCHOOL OF BUSINESS AND ECONOMICS

BACHELOR OF BUSINESS MANAGEMENT

COURSE CODE: BBM 479

COURSE TITLE: PROJECT MANAGEMENT

DATE: 26TH APRIL 2017			                                                 TIME: 2.00PM-4.00PM

INSTRUCTIONS TO CANDIDATES

- Answer question ONE (compulsory) and any other THREE

- Question one carries 25 marks

- All other questions carry 15 marks

This paper consists of 3 printed pages. Please turn over

QUESTION ONE

a) Explain the importance of the following when carrying out a feasibility study.

- Technical analysis                                                                        (4 marks)

- Social cost benefit analysis                                                       (4 marks)

b) Explain the qualities of a good project manager                                  (4 marks)

c) Describe three important features of a project                                    (3 marks)

d) Explain why communication is central to project management     (5 marks)

e) Briefly describe the stages associated with a project life cycle       (5 marks)

QUESTION TWO

a) Describe the possible types of conflicts that may arise during a project and five ways of handling these conflicts                                                 (9 marks)

b) Explain ways of handling the conflicts discussed in 2 (a) above     (6 marks)

QUESTION THREE

a) Describe the main activities that interface the main stages of the project life cycle                                                                                                         (12 marks)

b) Explain any three benefits of interim project evaluation over terminal project evaluation                                                                                            (3 marks)

QUESTION FOUR

A construction company is preparing a PERT network for laying the foundation of a new art museum. Given the following set of activities, their predecessor requirements and three estimates of completion time:

| Activity | Predecessor | Estimated duration in weeks |  |  |
| --- | --- | --- | --- | --- |
|  |  | Optimistic time | Pessimistic time | Most likely time |
| A | None | 2 | 4 | 3 |
| B | None | 8 | 8 | 8 |
| C | A | 7 | 11 | 9 |
| D | B | 6 | 6 | 6 |
| E | C | 9 | 11 | 10 |
| F | C | 10 | 18 | 14 |
| G | C, D | 11 | 11 | 11 |
| H | F, G | 6 | 14 | 10 |
| I | E | 4 | 6 | 5 |
| J | I | 3 | 5 | 4 |
| k | H, J | 1 | 1 | 1 |

Required:

- Draw the PERT network                                                                 (5 marks)

- Complete project duration and determine critical path     (10 marks)

QUESTION FIVE

XYZ Co Ltd is considering investing in one of the following two projects X and Y, which require an initial cash outlay of sh. 1,000,000.The cost of capital is 10%. The two projects would generate the following annual cash flows:

| Year | Project X (ksh.) | Project Y (ksh.) |
| --- | --- | --- |
| 1 | 150,000 | 200,000 |
| 2 | 400,000 | 350,000 |
| 3 | 450,000 | 400,000 |
| 4 | 450,000 | 400,000 |
| 5 | 200,000 | 100,000 |

You are required to advise the management on which of the two projects they should invest in using:

- Payback period                                                                        (5 marks)

- Net Present Value (NPV) method                                       (5 marks)

- Profitability Index (PI) method                                          (5 marks)