W1-2-60-1-6

JOMO KENYATTA UNIVERSITY OF AGRICULTURE AND TECHNOLOGY

# UNIVERSITY EXAMINATIONS 2014/2015

THIRD YEAR SECOND SEMESTER  EXAMINATION FOR THE DEGREE OF BACHELOR OF BUSINESS  INFORMATION TECHNOLOGY

BBT 2210 : PROJECT MANAGEMENT

DATE:   AUGUST   2015	                           	           TIME:   2 HOURS

INSTRUCTIONS:

ANSWER QUESTION ONE AND ANY OTHER TWO QUESTIONS

=========================================================

QUESTION ONE [COMPULSORY] [ 30 MARKS]

- Define  the term “PROJECT”  and  explain  the four  criteria  for the project to be considered successful.  [5 marks]

- The first step  in managing risk is to identify  the risks.  Describe five methods you could use for identifying  /uncovering  / revealing  risks.   									[5 marks]

- An IT  project has been running  well for 6 months. The IT  project manager  then noticed  a decrease  in the efficiency  and performance of the project team.  Describe  the steps they could take to deal with  this situation.  											[5 marks]

- Using  examples,  distinguish  between  WMS and PBS   [5 marks]

- Describe  five items that   should  be included   in a regular  progress report  to the project sponsor.      [5 marks]

- Outline  the  contents  of “Project  scope management plan”.

QUESTION TWO

A well known major political, party has decided to replace its  existing, in-house

membership  database with a passage-based  system.  It has  drawn up a short list

off four off-the-shelf packages, but  now meets  its outline  requirements

completely.  An outline plan  for the remaining  tests  in this project has been

drawn up as follows:

| Task | Description | Duration |
| --- | --- | --- |
| A | Compare the four packages and select one | 6 weeks |
| B | Amend this selected package | 10 weeks |
| C | Specify and design data for system testing | 6 weeks |
| D | Design and prepare a user training causes | 4 weeks |
| E | Design and develop a data migration program | 8 weeks |
| F | Carry out system testing | 3 weeks |
| G | Run the user training course | 4 weeks |
| H | Test the data migration program | 4 weeks |
| I | Carry out user acceptance testing | 3 weeks |
| J | Implement the replacement database system | 1 week |

Tasks B, C, D and E are all dependent  on Task A.  Task F cannot  start until task

B and C are both  completed.

Task G cannot start until  tasks B and D are both completed.

Task  H is solely  dependent  on task E.

Task I cannot  start until tasks F, G and H are all completed

Task J is dependent salary on  task I.

- Draw an  activity  on node diagram for this project, showing all dependencies  and the earliest   start time, latest finish  time, duration and float  for each task, highlight the critical path and calculate its duration. 										[10 marks]

- At the end of task A, it is realized  that task B can be reduced from 10 to 6 weeks, but task F  should be extended  from 3 to 5 weeks.  Re-calculate  all the earliest and latest   start times, and floats to reflect  these two changes and identify  any changes to the critical path.    [6 marks]

- In  some circumstances  a GANTT  chart might be used as an alternative to  a network diagram.

- Give two advantages , with a brief explanation  of each, of using a Gantt when compared with a network diagram.   [2 marks]

- Give two advantages with a brief explanation of  each, of using a network when compared  with a Gantt chart.  [2 marks]

QUESTION THREE

You  have reached the stage in a project where you have created a plan that shows

all the work  that needs done,.  You must  assign  resources to the tasks.

- Describe  five factor that you would consider  when allocation staff to a task.

[5 marks]

- You know that you have all the required  skills in the project  team but not enough people  with these skills to meet the project deadline.  What are some of the possible  actions you could  take?  [8 marks]

- It has been decided that you need to   hire a new member of staff for the project .  list the steps  that you need to go through from  identifying  the need for a new resource right  through the end of the recruitment process. 								 [7 mark]

QUESTION FOUR

You work for a small software house  which has  won a contract with a new  client

to design, develop and implement  a replacement database system.  The client is a

medical  research organization and has  very small IT section.  Your company has

a little  experience in this business area.   Your company has decided to use a new

rapid development method for this project and you  have been appointed project

manager.

- Define  the term “Project  Risk”   [1 mark]

- Give THREE examples of progress  risk that might affect your company  when undertaking the IT project describe  above.  [3 marks]

- List and explain  two factors used in evaluating risk exposure. Explain how each of these factors might  be assessed  quantitatively.   [4 marks]

- Risks can be assessed both quantitatively as above, and qualitatively.  Discuss the  way in  which risks could be assessed  quantitatively an dhow these qualitative  assessment could then be used to privilege risks.   [6 marks]

- Draw up a table illustrating the qualitative  assessment of risk exposure for the three  projects that you have  identified in part (a) above.   [6 marks]