W1-2-60-1-6

JOMO KENYATTA UNIVERSITY

OF

AGRICULTURE AND TECHNOLOGY

UNIVERSITY EXAMINATIONS 2014/2015

FIRST YEAR FIRST SEMESTER EXAMINATION FOR THE DEGREE OF MASTER OF SCIENCE IN CONSTRUCTION ENGINEERING AND MANAGEMENT

ECE 3181: CONSTRUCTION ENGINEERING AND MANAGEMENT

DATE:   AUGUST 2015		                                            TIME: 3 HOURS

INSTRUCTIONS:	ANSWER QUESTION ONE (COMPULSORY) AND ANY OTHER THREE QUESTIONS.  GRAPH PAPER IS PROVIDED

- Consider the project indicated on this table:

| Activity |  | Duration (Wks) | Direct Cost (mu) TOTAL | Labour (mu) | Materials (mu) | Plant (mu) |
| --- | --- | --- | --- | --- | --- | --- |
| A | 1 - 2 | 4 | 4,000 | 1,000 | 2,000 | 1,000 |
| B | 1 - 4 | 6 | 12,000 | 5,000 | 7,000 | - |
| C | 1 - 7 | 2 | 4,000 | 1,000 | 2,000 | 1,000 |
| D | 2 - 3 | 8 | 16,000 | 5,000 | 5,000 | 6,000 |
| E | 3 - 6 | 4 | 20,000 | 4,000 | 8,000 | 8,000 |
| F | 4 - 5 | 10 | 20,000 | 8,000 | 4,000 | 8,000 |
| G | 4 - 8 | 16 | 16,000 | 5,000 | 6,000 | 5,000 |
| H | 5 - 6 | 8 | 24,000 | 7,000 | 10,000 | 7,000 |
| I | 6 - 9 | 6 | 12,000 | 7,000 | 5,000 | - |
| J | 7 - 8 | 6 | 12,000 | 8,000 | 4,000 | - |
| K | 8 - 9 | 10 | 10,000 | 5,000 | 2,000 | 3,000 |

- General overheads are expected to 15% and profit 5% of direct costs.

- The contractor expects all payments to be delayed by 1 month.

- The client agrees to pay the contractors according to the contract as follows:

- 40% to be paid once activity F is completed.

- 40% when activity I is completed

- 15% at practical completion

- 5% after the end of 6 months maintenance period.

a)	Compute the cash flow, plot the cash flow curve and

compute the net interest to be charged the project

given that interest is 14% on borrowed money, and income

rate is 11%.  							[28.5 marks]

b)	Explain how this may change if the client had agreed to

pay 10% advance the contractor.				[1.5 marks]

- A construction company prepared its capital budget which included

3 contracts A, B, C which were already awarded, and a fourth one

which they were negotiating for, to commence in June, 2015.

The values of contract D is 198,000 monetary units (m.u.) with a

duration of 12 months.

Details of contracts A, B, C are as follows:

| Contract | Fixed Tender Price (m.u) | Period of construction |
| --- | --- | --- |
| A | 216,000 | 1st Jan. - 31st Dec, 2015 |
| B | 672,000 | 1st Jan. - 31st Dec, 2015 |
| C | 180,000 | 1st Jan. - 31st Dec, 2015 |

Each of these contracts includes an allowance to cover head

office overheads and profit as show below, which represent

10% of total tender sum.

| Contract | Head office overheads | Profit | Total |
| --- | --- | --- | --- |
| A | 9,600 | 12,000 | 21,600 |
| B | 28,000 | 39,200 | 67,200 |
| C | 9,000 | 9,000 | 18,000 |
| D | 6,600 | 13,200 | 19,800 |
| Total | 53,200 | 73,400 | 126,600 |

Six months later, a review is made for the projects, and as

on 30th June, 2015, the following was the position:

| Contract | Value of work done | Direct cost to date | Overheads to date | Profit to date |
| --- | --- | --- | --- | --- |
| A | 108,000 | 100,800 | 4,800 | 6,000 |
| B | 336,000 | 308,000 | 14,000 | 19,600 |
| C | 75,000 | 60,000 | 4,500 | 4,500 |
| D | Contract awarded to others |  |  |  |

- Prepare a budget for the year 2015, assuming costs can

be spread uniformly throughout the year.			[8 marks]

- Compute the company sales (revenue) and overhead

variances and the total variances on each contract at

30th June 2015.  Hence obtain the actual profit and

compute profit variance.					[10 marks]

- Advice management on action to take.			[2 marks]

- a)	For the project shown, analyse the network for early and

late times and the floats.  Establish the resource requirements

if the project were to start early as possible.  Comment on

your results.							[15.5 marks]

b)	Given that the resource C is limited to 7 and L is unlimited

establish the resource requirements taking the early start as

the major sort with the total float as the minor sort.	[4.5 marks]

| Activity | Duration | Dependency | Resource Requirement |
| --- | --- | --- | --- |
| A | 5 | Start | 4C, 3L |
| B | 10 | Start | 5C, 2L |
| C | 0 | A | -, - |
| D | 10 | A | 2C, 7L |
| E | 5 | B | 3C, 6L |
| F | 4 | B | 4C, 5L |
| G | 5 | C | 3C, 6L |
| H | 8 | E | 5C, 3L |
| I | 9 | F | 4C, 7L |

- a)   Discuss Hammocks and ladders in Networks.	[4 marks]

b)	Discuss advantages or otherwise of precedence

(activity on Node) diagrams over activity on Arrow

diagrams.	[5 marks]

c)	Discuss the main purpose of cash flow in a project and

the main ingredients in the determination of cash flow.	[6 marks]

d)	Discuss SIX sigma in relation to dimensions of

performance.	[2 marks]

e)	Define Economic Order Quantity (EOQ).  What are the

underlying assumptions in arriving at EOQ?	[3 marks]

- a) 	Define “Operations Research”					  [1.5 marks]

b)	Discuss the significant features of operations.		  [5.5 marks]

c)	Discuss the steps required for analysis of a problem

under operations research.					   [4.5 marks]

d)	What ate the limitations of operations research? 		   [4.5 marks]

e)	State the types of organization structures that there may

be in construction.  Briefly discuss the advantages and

disadvantages of any of them.					   [4 marks]

6. 	a)	Differentiate between equity and debt.			   [1.5 marks]

b)	Discuss the sources of funding that a contractor may have from:

(i)	Capital markets						  [10 marks]

(ii)	Leasing							  [8.5 marks]