# UNIVERSITY OF KABIANGA

UNIVERSITY EXAMINATIONS

2014/2015 ACADEMIC YEAR

THIRD YEAR SECOND SEMESTER EXAMINATION

FOR THE DEGREE OF BACHELOR OF SCIENCE IN AGRO-FORESTRY AND RURAL DEVELOPMENT

COURSE CODE: FOR 325

COURSE TITLE: FOREST BUSINESS MANAGEMENT

DATE: 21ST APRIL, 2015                                                                                            TIME: 9 A.M- 12 P.M

INSTRUCTIONS:

ANSWER QUESTION ONE AND ANY OTHER THREE QUESTIONS.

Question One

- Define management and outline its functions. (7 marks)

- Briefly discuss the three main styles of management. (9 marks)

- Explain the differences between theory X, theory Y and theory Z in management. (9 marks)

Question Two

- What makes a forest product useful? (3 marks)

- Discuss the marketing mix decisions and how they can be used to improve marketing of forest products. (6 marks)

- Outline the marketing research process. (6 marks)

Question Three

- State the applications of linear programming in forestry. (10 marks)

- Explain the limitation of linear programming. (5 marks)

Question Four

Write brief notes on the following issues as regards management.

- Challenges for business managers in the global environment. (8 marks)

- Agricultural business risks and their analysis. (7 marks)

Question Five

- Outline the advantage and limitations of the Critical Path Management (CPM) and Program Evaluation and Review Technique (PERT). (3 marks)

- The table below defines the activities within a medium scale forestry project.

| Activity | Completion time (weeks) | Immediate predecessor (activities) |
| --- | --- | --- |
| A | 3 | - |
| B | 1 | A |
| C | 2 | B, A |
| D | 7 | - |
| E | 8 | D, A |
| F | 3 | B |
| G | 1 | E, F |
| H | 2 | D |

- Draw the network diagram. (4 marks)

- Calculate the minimum overall completion time and identify which activities are critical. (4 marks)

- What is the slack (float) time associated with each of the non-critical activities. (4 marks)