MERU UNIVERSITY OF SCIENCE AND TECHNOLOGY

P.O. Box 972-60200 – Meru-Kenya.

Tel: 020-2069349, 061-2309217. 064-30320 Cell phone: +254 712524293, +254 789151411

Fax: 064-30321

Website: www.must.ac.ke  Email: info@must.ac.ke

University Examinations 2015/2016

THIRD YEAR FIRST SEMESTER EXAMINATION FOR DIPLOMA IN CIVIL ENGINEERING

ECV 2306: PROJECT MANAGEMENT II

DATE: NOVEMBER 2015					   	                 TIME: 11/2 HOURS

INSTRUCTIONS: Answer question one and any other two questions

QUESTION ONE (30 MARKS)

- Define the following terms:

- Project.

- Work breakdown structure.

- Project management

- Critical path.

- Resource leveling. 								(5 Marks)

- Explain causes of delays in project management.					(5 Marks)

- Explain the three mechanisms of project control.					(3 Marks)

- Identify the objectives and functions of construction management.		(5 Marks)

- Explain the differences between a CPM and PeRT methods.			(6 Marks)

- Describe the advantages of scheduling.						(4 Marks)

- Explain any two uses of a Ganit chart in management construction projects.	(2 Marks)

QUESTION TWO (15 MARKS)

Given the following information:

| Activity | Preceding activities | Duration |
| --- | --- | --- |
| A | - | 7 |
| B | - | 6 |
| C | A,B | 13 |
| D | A,B | 6 |
| E | B | 12 |
| F | D,E | 7 |
| G | C,F | 10 |
| H | D,E | 5 |
| I | G,H | 6 |

- Draw the A.O.A diagram to determine the critical path and project duration.	(7 Marks)

- For all the non critical activities, determine the following:

- Total float.

- Free float.

- Independent float

- Slack.									(8 Marks)

QUESTION THREE (15 MARKS)

- Define the following terms:

- Earliest start time.

- Latest start time.

- Earliest finish time.

- Latest finish time.

- Dummy.									(5 Marks)

- Explain the following terms as used in PERT method of scheduling:

- Most likely time.

- Pessimistic time.

- Optimistic time								(3 Marks)

- Discuss the limitations of network analysis.					(5 Marks)

- Explain any two major differences between A.O.A and A.O.N networks.	(2 Marks)

QUESTION FOUR (15 MARKS)

- Explain the term project control.							(1 Mark)

- Describe any five characteristics of project control mechanism.			(5 Marks)

- Identify the common issues faced in project control.				(5 Marks)

- Identify the core resources for project control.					(4 Marks)